6. Implementation Plan

CoffCo Coffee Machine

Applied Systems Engineering Certificate Deliverable 6

| Field | Detail |
| --- | --- |
| Document Reference | 6. Implementation Plan CoffCo Coffee Machine V1.0 |
| Issue | 1.0 |
| Date | June 2026 |
| Prepared by | CoffCo Systems Team / School of Systems Engineering Secondment |
| Approved by | Pending — Systems Design Authority (SDA) |
| Related Documents | System Requirements Specification CoffCo Coffee Machine V3.0 ¦ System Architecture CoffCo Coffee Machine V2.2 ¦ System Design Description CoffCo Coffee Machine V1.1 |

# Document History

| Issue | Date | Author | Description | Approved |
| --- | --- | --- | --- | --- |
| 1.0 | June 2026 | CoffCo / SSE | Initial issue. Implementation approach previously embedded in SE Proposal. Extracted and structured as a dedicated deliverable to meet DoD 6 requirements. | Pending |

# 1. Introduction and Scope

This document defines the implementation plan for the CoffCo in-room hotel coffee machine MVP. The system will not be fully manufactured on this programme — the objective is to demonstrate to Vacation Stables and investors that the design is sufficiently mature and de-risked to support investment commitment and proceed to physical build. The plan describes the prototype/MVP approach, make/buy decisions, key suppliers, required resources, and the link to the Through Life Support theme.

## 1.1 Implementation Scope

- Single prototype unit for investor demonstration and Vacation Stables CEO approval

- MVP functional scope: americano brewing, hot frothed milk production, volume selection, status indication, wireless maintenance telemetry

- Physical build: 3D printed / CNC machined chassis and casing (acceptable for MVP); certified PSU and production-representative PCBA for control assembly

- Certification: IEC 60335-1 type-test, CE/UKCA/UL marking, EN 55014 EMC — required before first hotel deployment, not for investor MVP

- Out of scope: full-scale manufacturing; consumable supply chain (commercial arrangement); guest loyalty app integration (future increment)

# 2. Build Strategy — Prototype to Production

| Phase | Description | Output | Entry Gate |
| --- | --- | --- | --- |
| P0 — Design Freeze | Complete systems engineering baseline. SRS Issue 3.0, ARCH v2.2, SDD V1.1 baselined. All architecture decisions taken. Open technical decisions resolved except TD-06 (wireless). | Baselined document suite (this programme). CN-003 issued. | SDA sign-off on SRS/ARCH/SDD baseline |
| P1 — Component Selection | Source and verify all COTS components. PSU supplier selected and surge-tested. Watchdog IC and TCO sourced. PRV type selected. PCB layout completed. | Component BOM with verification data. COTS supplier quals. | COTS component test certificates received |
| P2 — Prototype Build | Single functional prototype. 3D printed chassis. Production PCBAs. All safety-critical hardware fitted (TCO, WDT IC, PRV, fuse). Firmware loaded. | Working prototype unit. Phase 2 test cases executed (TC-008, TC-HE-01, TC-FW-01, TC-PRV-01). | All Phase 2 safety tests PASS |
| P3 — Integration and V&V | Integrate all subsystems. Execute V&V test programme per COFFCO-VVP-001. Telemetry verified. Milk spoilage, drip tray, descale alerts verified. | Completed test records (Phase 3–4). V&V certificate. | All Phase 3–4 tests PASS; SDA witness sign-off |
| P4 — Investor / Customer Demo | Demonstrate to Vacation Stables CEO and investors in hotel room simulation environment. Validation events VE-D1 and VE-B1. | Customer acceptance sign-off. Investor demonstration package. | Vacation Stables CEO accepts; investor commitment confirmed |
| P5 — Certification | IEC 60335-1 type-test at accredited third-party facility. EN 55014 EMC test. CE/UKCA/UL marking obtained. | Type-test certificate. Declaration of Conformity. | Before first hotel room deployment |

# 3. Make / Buy Decisions

The make/buy strategy is governed by the Through Life Support theme: COTS components from established, multi-sourced, pre-certified suppliers reduce technical risk, reduce certification burden, and provide proven reliability data. Bespoke design is applied only where no COTS option meets the functional or interface requirement.

| Assembly / Element | Decision | Key Supplier / Source | Rationale |
| --- | --- | --- | --- |
| Control Assembly (PCBA) | Buy (contract manufacture) | Contract PCB assembly house (TBD) to CoffCo design | CoffCo controls design IP; contract manufacture reduces tooling investment and build risk at MVP volumes |
| Wireless module | Buy (COTS) | TBD — pending TD-06 resolution (Wi-Fi / BLE / Zigbee) | Wireless module is a commodity; certification and driver support included with COTS module |
| Thermal Assembly (fluid path, frother) | Make (CoffCo bespoke) | CoffCo-designed; heating element from specialist supplier (COTS) | Fluid path arrangement and cross-contamination prevention are core IP. Heating element from COTS. |
| Power Supply Unit | Buy (COTS certified) | Universal switch-mode PSU module (e.g. Mean Well, XP Power) | Certified COTS PSU transfers IEC 60335 electrical safety compliance risk to established supplier |
| Interchangeable plug module | Make (CoffCo bespoke) | Designed by CoffCo; injection moulded externally | Plug format is market-specific; interchangeable design (TD-03) minimises SKU complexity |
| Structural chassis and casing | Buy (injection moulded to CoffCo design) | Injection moulding subcontractor; recycled polymer specification | CoffCo controls geometry; manufacturing outsourced. Recycled polymer per SRS 3.4 (≥50% recycled content). |
| Thermal Cutoff (TCO) | Buy (COTS safety device) | Cantherm or Emerson bi-metallic TCO (100°C / 250V / 10A) | Mature, multi-sourced safety device. Non-resettable. Certified to IEC 60691. Mandated by SRS 3.10. |
| Hardware Watchdog IC | Buy (COTS) | Maxim DS1232 or equivalent | High-volume, multi-sourced. Validated 1.6s timeout programmable. Mandated by SRS 3.12. |
| Pressure Relief Valve | Buy (COTS food-grade) | Parker or Watts food-grade PRV (2.5 bar, food-grade wetted parts) | Commodity safety device; food-grade materials required by SRS 4.9. Mandated by SRS 3.13. |
| Mains fuse | Buy (COTS) | Littelfuse or Schurter 5×20mm T-type IEC 60127 | Commodity component. Mandated by SRS 3.11. Rating confirmed at detail design against peak load. |
| Coffee consumables | Commercial arrangement | CoffCo supply partner (TBD) | Out of system design scope. Commercial arrangement to be agreed with Vacation Stables. |

# 4. Resources and Facilities

| Resource / Facility | Purpose | Notes |
| --- | --- | --- |
| Electronics assembly bench | PCBA build and rework; component fitting | Surface-mount soldering equipment; ESD protection |
| Thermal cycling rig | Thermal assembly verification; brew temperature testing | Calibrated thermocouple (±0.5°C); pressure gauge at outlet |
| Pressure test bench | PRV verification (TC-PRV-01); extraction pressure verification | Calibrated bench pump; pressure gauge to 5 bar |
| EMC test chamber (external) | EN 55014 Class B radiated emission testing | Accredited third-party facility; booked at Phase 4–5 |
| IEC 60335 test laboratory (external) | Type-test for CE/UKCA/UL certification | Accredited third-party facility required. See V&V Plan Phase 5. |
| Hotel room simulation environment | Integration testing; validation events VE-D1 and VE-B1 | Mock hotel room with representative furniture, mains supply, wireless network |
| Water hardness test kit (0–500 mg/L CaCO₃) | SRS 1.6 water hardness tolerance verification | Required to set descale interval calibration baseline |
| Vacation Stables water quality data | SRS 1.6 hardness range threshold confirmation | Data request to Vacation Stables estate management — outstanding dependency D-04 |
| CoffCo cloud platform | Telemetry verification; maintenance alert testing | Development environment for Phase 3 telemetry tests |
| Debug interface (JTAG/SWD) | Firmware watchdog test (TC-FW-01); in-circuit test | Required to simulate firmware hang for watchdog verification |

# 5. Through Life Support — Implementation Linkage

The make/buy strategy directly expresses the Through Life Support theme. Every supplier and component choice is evaluated against its reliability impact.

- COTS PSU from a certified manufacturer transfers IEC 60335 electrical safety compliance risk to an established supply chain with known MTBF data. This directly supports SRS 3.9 (MTBF ≥26,280 hours).

- The thermal assembly is designed in-house because the thermal path and cross-contamination prevention are the primary CoffCo reliability differentiators — these must be under direct engineering control.

- All safety devices (TCO, WDT IC, PRV, fuse) are specified as multi-sourced COTS components. Single-source safety components create supply chain risk that undermines long-term reliability and repairability.

- The interchangeable plug module (TD-03) isolates the component most vulnerable to regulatory change (power connector standards evolve by market) from the rest of the assembly — a direct application of SP-02 (Modularity) for reliability.

- 3D printing and CNC machining for the prototype chassis is explicitly accepted as not production-representative. The transition from prototype chassis to injection-moulded production chassis is a planned design review gate before first hotel deployment.

# 6. Definition of Done — Compliance

The following table confirms compliance with the Applied Systems Engineering Certificate DoD 6 criteria.

| Definition of Done Criterion | Status | Evidence |
| --- | --- | --- |
| Implementation scope and objectives defined (what will be built, integrated, or procured) | PASS | Section 1.1 — 6-point scope definition; in-scope and out-of-scope explicitly stated |
| Implementation approach described (Make/Buy decisions, key suppliers, technology choices) | PASS | Sections 2 and 3 — 6-phase build strategy; 11-row Make/Buy table with rationale for each |
| Required resources and environments identified (labs, tools, test rigs, data, facilities) | PASS | Section 4 — 10-row resources table with purpose and notes for each |