## Document History
COFFCO-HAZID-001 — Hazard Identification Register ¦ Document History
Issue | Date | Author | Description of Change | CN Reference | Approved By
1.0 | June 2026 | CoffCo / SSE | Initial issue. 19 hazards (H-01 to H-19) identified using structured guide-word HAZID review of all six subsystems (SS-1 to SS-6). MIL-STD-882E qualitative risk matrix applied. All residual risks LOW or MEDIUM. 17 safety-derived requirements (SAF-01 to SAF-17) identified. | — | SDA
2.0 | June 2026 | CoffCo / SSE | SAF requirement IDs replaced throughout with consolidated COFFCO-SRS-001 Issue 3.0 requirement identifiers (SRS 3.10, 3.11, 3.12, 3.13 etc.). Safety Requirement Traceability sheet added showing former SAF-to-SRS mapping. 'New Safety Requirements' sheet removed (content now in COFFCO-SRS-001 Issue 3.0). Module and course references removed. | CN-003 | SDA

## HAZID
COFFCO HAZID — COFFCO-HAZID-001 ¦ Issue 1.0 ¦ Project: CoffCo MVP ¦ Prepared by: Systems Design Authority
MIL-STD-882E qualitative risk matrix applied. Risk Score = Probability × Severity (1–5 × 1–4). HIGH ≥12 ¦ SERIOUS ≥6 ¦ MEDIUM ≥3 ¦ LOW <3
ID | Node / Subsystem | Hazard Name | Cause | Effect / Consequence | Initial Probability | Initial Severity | Initial Risk Score | Initial Risk Level | Mitigation / Safeguard | Residual Probability | Residual Severity | Residual Risk Score
H-01 | SS-2 Brew Control (Thermal Assembly) | Heating Element Runaway | Thermal control firmware failure; thermocouple degradation; stuck relay | Fluid temperature exceeds 90°C; risk of steam pressure release and scalding burn to user at dispensing outlet | Occasional | Critical | 9 | SERIOUS | Independent bi-metal thermal cutoff (non-resettable at ≥100°C); firmware temperature watchdog with dual-sensor cross-check; fault state blocks brew command (SRS 1.7, 3.10). Requirement: SRS 3.10. | Improbable | Marginal | 2
H-02 | SS-2 Brew Control (Thermal Assembly) | Dry-Fire / Empty-Store Brew Initiation | Fluid level sensor fault or user empties reservoir between cycles; brew command issued with insufficient fluid | Heating element energised without water cooling; element burns out; possible secondary fire or chassis deformation | Occasional | Critical | 9 | SERIOUS | Fluid level interlock: firmware inhibits heating element activation when level sensor < minimum threshold; fault state entered; UI indicates EMPTY (SRS 1.10, SRS 1.7). Requirement: SRS 1.10. | Improbable | Marginal | 2
H-03 | SS-3 Fluid Store | Internal Fluid Path Leak | Seal/gasket degradation; over-pressure burst at fittings; mechanical damage during servicing | Hot pressurised fluid contacts low-voltage PCB; potential short circuit; fire/smoke hazard in hotel room | Remote | Catastrophic | 8 | SERIOUS | All fluid pathways routed in dedicated sealed thermoplastic channel, physically separated from all electrical components; IEC 60335 IPX4 splash protection; annual seal inspection in service schedule (SRS 3.10, 4.8). Requirement: SRS 3.11. | Improbable | Critical | 3
H-04 | SS-4 Power Management (PSU) | Mains Voltage Exposure to User | Double-insulation failure; mechanical casing fracture; incorrect housekeeping handling causing enclosure damage | Electric shock to hotel guest or housekeeping staff; potential fatality | Remote | Catastrophic | 8 | SERIOUS | IEC 60335 Class II double insulation; no accessible live parts; Structural Chassis acts as secondary enclosure; tamper-evident fasteners; RCD/GFCI protected hotel circuits assumed (SRS 3.11, 4.8). Requirement: SRS 3.11. | Improbable | Marginal | 2
H-05 | SS-4 Power Management (PSU) | Overvoltage / Surge Input | Hotel mains transient; lightning; switching surge; incorrect voltage connection (US 120 V vs EU 230 V) | PSU component failure; potential arcing; downstream component damage; fire ignition | Occasional | Critical | 9 | SERIOUS | Universal AC input 100–240 V, 50/60 Hz (SRS 2.2, 2.3); MOV transient voltage suppressor; IEC 60335 overvoltage tested; fused primary side. Requirement: SRS 2.3. | Improbable | Marginal | 2
H-06 | SS-1 User Interface (HMI Panel) | Inappropriate Use / User Error Leading to Burn | Guest places hand under dispensing outlet during active brew; child accesses machine unsupervised | Hot beverage (60–90°C) contacts hand causing first- or second-degree scalding burn | Probable | Marginal | 8 | SERIOUS | Dispensing outlet shrouded; no accessible hot surfaces (SRS 3.10); UI status light clearly indicates BREWING state; dispense only into cup placed in drip zone (physical guide). Requirement: SRS 3.10. | Remote | Negligible | 2
H-07 | SS-2 Brew Control (Control Assembly) | Software / Firmware Runaway State | Memory corruption; watchdog timer failure; electromagnetic interference causing firmware hang | Uncontrolled brew cycle; heating or dispensing unable to stop; overflow or thermal hazard | Remote | Critical | 6 | SERIOUS | Hardware watchdog timer independent of main MCU; power-cycle-only recovery (fail-safe OFF); all actuators default to de-energised on reset; EMC per EN 55014 Class B (SRS 3.8). Requirement: SRS 3.12. | Improbable | Marginal | 2
H-08 | SS-3 Fluid Store (Milk Refrigeration) | Milk Spoilage / Food Safety Failure | Refrigeration unit failure; ambient temperature rise; prolonged power outage; housekeeping failure to replenish | Spoiled milk dispensed to guest; food poisoning risk (Salmonella, Listeria) | Occasional | Critical | 9 | SERIOUS | Refrigeration temperature monitoring (SS-5); alert transmitted to cloud ops dashboard if milk store >4°C for >30 min; HACCP plan mandates daily housekeeping milk check; UI LOW-CONSUMABLE alert (SRS 1.4, 1.7, NR-05). Requirement: SRS 1.9. | Improbable | Marginal | 2
H-09 | SS-2/SS-3 (Cross-contamination) | Coffee-Milk Cross-Contamination | Inadequate automated flush between americano and milk-froth cycles; seal failure in fluid switching valve | Dairy residue in coffee path; allergen exposure for lactose-intolerant guests; food safety breach | Occasional | Marginal | 6 | SERIOUS | Automatic flush cycle between product paths; food-grade elastomer seals; HACCP documentation (NR-04, SRS 4.9). Existing control. Residual acceptable. | Improbable | Negligible | 1
H-10 | SS-5 Monitoring & Comms | Telemetry Failure / Loss of Remote Monitoring | Wireless link failure (TD-06 unresolved); cloud platform outage; firmware bug in telemetry stack | Loss of fault visibility; delayed maintenance response; machine operates in degraded state unknown to hotel ops | Occasional | Marginal | 6 | SERIOUS | Local fault state displayed on UI regardless of comms (SRS 1.7); telemetry failure triggers ops dashboard alert; fallback to scheduled inspection if comms offline >24 h. Requirement: SRS 1.9. | Remote | Negligible | 2
H-11 | SS-6 Structural Chassis | Machine Tip-Over / Instability | Guest pulling machine forward; cord entanglement; uneven surface; mounting not to shelf standard | Machine falls; hot fluid spills; electrical connector exposed; injury to guest | Remote | Critical | 6 | SERIOUS | Centre-of-gravity design target ≤10 kg with low CoG (SRS 4.10); anti-tip bracket provision for wall/shelf mounting; cord management channel. Requirement: SRS 4.10. | Improbable | Marginal | 2
H-12 | SS-6 Structural Chassis + SS-4 PSU | Overheating of Enclosure / Fire | Blocked ventilation slots; external heat source (e.g. direct sunlight); extended idle-heat soak | Chassis surface temperature exceeds safe-touch limits; internal component temperature rise; potential ignition of surrounding soft furnishings | Remote | Critical | 6 | SERIOUS | Chassis ventilation slot design per IEC 60335 thermal requirements; maximum surface temperature ≤48°C (touch safety); thermistor on enclosure wall linked to fault-state shutdown. Requirement: SRS 3.10. | Improbable | Marginal | 2
H-13 | SS-2 Thermal Assembly (Pressure Circuit) | Fluid System Overpressure | Pump control failure (open); blocked dispensing outlet or filter; scale blockage; dispensing valve solenoid stuck closed; thermal expansion in sealed fluid path | Pressurised hot water system exceeds design limits; pressure vessel or fitting failure; scalding fluid/steam release at burst point; potential injury to user or housekeeping | Occasional | Critical | 9 | SERIOUS | Mechanical pressure relief valve (PRV) fitted in the fluid circuit, rated to open at ≤2.5 bar (≤2× maximum operating pressure), venting safely into the drip tray. PRV is hardware-only, independent of firmware and pump control. Pump COTS selection limited to ≤1.3 bar rated output. Pressure transducer monitors in-circuit pressure; firmware shuts pump if >1.5 bar (FW-SF-08). Requirement: SRS 3.13. | Improbable | Marginal | 2
H-14 | SS-4 Power Management (Mains Input Circuit) | Mains Overcurrent — No Fuse Protection | Internal wiring short-circuit; component failure causing low-impedance fault to chassis or earth; insulation breakdown under single fault; mains connector fault | Sustained overcurrent fault not interrupted; mains wiring or PSU component reaches ignition temperature; fire risk within machine or hotel room; hotel RCD may not trip fast enough without a fuse limiting fault current | Remote | Catastrophic | 8 | SERIOUS | Mains input fuse fitted at or immediately after the inlet point, rated to the minimum value that protects the cable and PSU primary (typically 5–10 A T-type, sized to load plus 20% margin). Fuse is accessible to field engineer only (not hotel guests). Fuse rating and type documented in COTS Decision Log and COFFCO-SDD-001. Compliant with IEC 60335-1 Clause 25 (abnormal operation). Requirement: SRS 3.11. | Improbable | Marginal | 2
H-15 | SS-4 PSU + SS-6 Chassis (External Water Ingress) | External Water Ingress During Cleaning | Housekeeping uses wet cloth or spray cleaning agent on machine exterior; overfilled drip tray spills water toward base vents or cable entry; water ingress into mains or low-voltage circuit | Water contacting live mains conductors inside PSU or chassis; electric shock to housekeeping staff; short circuit; fire | Occasional | Critical | 9 | SERIOUS | Machine enclosure rated IPX2 minimum (drip-proof) per IEC 60335-1 Annex A; all base ventilation slots angled to prevent direct water ingress; housekeeping SOP specifies damp cloth only, no spray cleaning; drip tray capacity and FULL indicator designed to prevent overflow before service visit. Requirement: SRS 3.11. | Improbable | Marginal | 2
H-16 | SS-3 Fluid Store (Drip Collector / Tray) | Drip Tray Overflow | Drip tray not emptied during housekeeping; extended high-usage period causes tray to fill and overflow; water tracks onto hotel furniture surface or into machine base | Water damage to hotel furniture (commercial liability); water ingress to machine base creating electrical hazard; guest slipping on wet surface | Probable | Marginal | 8 | SERIOUS | Drip tray capacity designed for minimum 5 full brew cycles between empties; FULL sensor or visual indicator triggers LOW-CONSUMABLE status on UI and telemetry alert; housekeeping SOP includes daily drip tray check. Requirement: SRS 1.7/1.9. | Remote | Negligible | 2
H-17 | SS-2 Thermal Assembly + SS-3 Fluid Store (Scale Accumulation) | Scale Build-Up Causing Flow Restriction and Pressure Fault | Hard water calcium carbonate deposits accumulate in heating element, filter, fluid pathway, or pump over time; progressive flow restriction increases system pressure; PRV activation or tube joint failure at weakest point | PRV activation vents hot water into drip tray (acceptable) OR if PRV fails to open, weakest tube joint bursts causing scalding fluid release; long-term element damage if scale insulates heating surface causing element overheat | Probable | Critical | 12 | HIGH | Automatic descale cycle triggered by firmware at interval based on water hardness setting and brew count (SRS 1.6 water hardness tolerance is the driver); scale status transmitted via telemetry to trigger proactive field service before restriction reaches critical level; water filter in SS-3 reduces incoming hardness (SRS 1.6). PRV (H-13, SRS 3.13) is hardware backstop against pressure fault. Requirement: SRS 1.6. | Remote | Marginal | 4
H-18 | SS-3 Fluid Store (Consumable Loading) | Incorrect or Forced Consumable Loading | Hotel guest inserts wrong consumable format, oversized item, or non-CoffCo-format consumable into extraction chamber; guest forces door/holder closed; extraction chamber seal breached or damaged | Seal failure at extraction chamber during brew; hot pressurised water escapes at breach point; scalding injury; machine inoperable pending field service | Remote | Critical | 6 | SERIOUS | Consumable holder designed with keyed geometry accepting only correct format (implementation-neutral: applies to capsule, pod, or ground-coffee basket as applicable to selected design); clear LOAD INDICATOR on UI; extraction door includes mechanical interlock preventing close if consumable not correctly seated. Foreseeable misuse per IEC 60335-1 Clause 21. Requirement: SRS 1.4. | Improbable | Marginal | 2
H-19 | SS-1 User Interface + SS-2 Thermal (Child Interaction) | Child Misuse — Control Activation and Reach Hazard | Young child in hotel room activates brew cycle unsupervised; reaches dispensing outlet; attempts to pick up or pull machine | Child receives hot beverage at dispensing outlet (scalding burn); child tips machine (H-11 already covers tip-over but adult force assumed); child accidentally initiates brew creating burn hazard during active cycle | Remote | Critical | 6 | SERIOUS | Brew initiation requires deliberate two-step action (select drink type THEN confirm) reducing accidental activation; dispensing outlet shroud (SRS 3.10) prevents direct contact with beverage stream regardless of user age; tip-over bracket (SRS 4.10) prevents tipping under child-equivalent force; machine height and control placement on front face reviewed against IEC 60335-1 Annex A child misuse requirements. No additional SRS required — SRS 3.10, SRS 4.10, and HMI design govern. Note recorded in safety case for IEC 60335-1 Annex A compliance evidence. | Improbable | Marginal | 2

## Risk Matrix (MIL-STD-882E)
CoffCo HAZID — MIL-STD-882E Qualitative Risk Matrix
Probability \ Severity | Catastrophic (4) | Critical (3) | Marginal (2) | Negligible (1)
Frequent (5) | HIGH (20) | HIGH (15) | SERIOUS (10) | MEDIUM (5)
Probable (4) | HIGH (16) | HIGH (12) | SERIOUS (8) | MEDIUM (4)
Occasional (3) | HIGH (12) | SERIOUS (9) | SERIOUS (6) | MEDIUM (3)
Remote (2) | SERIOUS (8) | SERIOUS (6) | MEDIUM (4) | LOW (2)
Improbable (1) | MEDIUM (4) | MEDIUM (3) | LOW (2) | LOW (1)

## Safety Requirement Traceability
COFFCO-HAZID-001 Issue 2.0 — Safety Requirement Traceability ¦ Former SAF IDs → Consolidated SRS 3.0 Requirements
Hazard | Former ID | Consolidated SRS Requirement | What Changed | Verification Method | HAZID H-ref
H-01 | SAF-01 | SRS 3.10 — Burn prevention | TCO device requirement incorporated into SRS 3.10 acceptance criteria | Inspection + Test (TC-HE-01) | H-01
H-02 | SAF-02 | SRS 1.10 — Dry-fire prevention | 5-second response time and auto-recovery merged into SRS 1.10 | Test (TC-008) | H-02
H-03 | SAF-03 | SRS 3.11 — Electrical shock prevention | 6 mm fluid/electrical isolation incorporated into SRS 3.11 acceptance criteria | Inspection | H-03
H-04 | SAF-04 | SRS 3.11 — Electrical shock prevention | IEC 60335-1 Class II incorporated into SRS 3.11; also SRS 4.8 | Analysis (type test) | H-04
H-05 | SAF-05 | SRS 2.3 — UK/EU power supply | IEC 61000-4-5 surge test incorporated into SRS 2.3 acceptance criteria | Test (PSU cert.) | H-05
H-06 | SAF-06 | SRS 3.10 — Burn prevention | Dispensing outlet shroud incorporated into SRS 3.10 acceptance criteria | Inspection | H-06
H-07 | SAF-07 | SRS 3.12 — Firmware watchdog (NEW) | No existing requirement covered this. SRS 3.12 added as new requirement | Test (TC-FW-01) | H-07
H-08 | SAF-08 | SRS 1.9 — Maintenance status comms | MILK-SPOILAGE-RISK telemetry incorporated into SRS 1.9 | Test + Demo | H-08
H-10 | SAF-09 | SRS 1.9 — Maintenance status comms | Comms watchdog / COMMS-FAULT incorporated into SRS 1.9 | Demonstration | H-10
H-11 | SAF-10 | SRS 4.10 — System mass and stability | Anti-tip bracket and 50N stability test incorporated into SRS 4.10 | Test | H-11
H-12 | SAF-11 | SRS 3.10 — Burn prevention | 48°C surface temperature limit incorporated into SRS 3.10 acceptance criteria | Test | H-12
H-13 | SAF-12 | SRS 3.13 — Pressure relief valve (NEW) | No existing requirement covered over-pressure protection. SRS 3.13 added | Inspection + Test (TC-PRV-01) | H-13
H-14 | SAF-13 | SRS 3.11 — Electrical shock prevention | Mains fuse requirement incorporated into SRS 3.11 | Inspection | H-14
H-15 | SAF-14 | SRS 3.11 — Electrical shock prevention | IPX2 enclosure rating incorporated into SRS 3.11 | Test (TC-IPX2-01) | H-15
H-16 | SAF-15 | SRS 1.7 / SRS 1.9 — Status / comms | Drip tray full sensor alert incorporated into SRS 1.7 and 1.9 | Test + Demo | H-16
H-17 | SAF-16 | SRS 1.6 — Water hardness / descale | Descale scheduling incorporated into SRS 1.6 | Test + Demo | H-17
H-18 | SAF-17 | SRS 1.4 — Consumable capacity / interlock | Consumable interlock incorporated into SRS 1.4 | Inspection + Test | H-18
H-19 | (none) | SRS 3.10 + SRS 4.10 cover this hazard | No new requirement needed — covered by shroud (3.10) and stability (4.10) | See SRS 3.10 / 4.10 tests | H-19